## Sheet1
# | Reported Date | Report By | Severity [P0-P5] | Statues [open, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 - dash bug | 2024-10-03 | 2024-10-12 | P1 | Resolved | Sky | Player disappears if dash in place | Player will dash in last direction if in place, bottom-right by default | player disappears if dash is used without any directional keys | press space to dash while staying still
2 - collision circle persists after enemy dies | 2024-10-06 | 2024-10-12 | P3 | Resolved | Amanda | collision circle persists after enemy dies | collision circle will disappear after enemy disappears | collision circle persists after enemy dies | kill enemy by shooting bullets
3- Removing bullets causes game crash | 2024-10-05 | 2024-10-12 | P0 | Resolved | Everyone | Removing bullets causes an assertion in get to fail, crashing the game | Bullet is removed (no longer rendered and tracked) and game continues as normal | When bullet is removed the game immediately crashes with an assertion error | shoot while bullet range is enabled
4 - dash bug 2 | 2024-10-07 | 2024-10-12 | P3 | Resolved | Dean | Player can dash through line walls | Can't dash through wall | can dash through wall if player collider is small enough | dash toward wall when near wall
5 - Random game crashes on enemy death | 2024-10-06 | 2024-10-12 | P0 | Resolved | Everyone | Enemies dying can sometimes cause an assertion fail and crash the game | Enemy dies and is removed, game continues | The enemy dying in a certain way will cause the game to crash, such as A) player bullet kills enemy and hits wall simultaneously, and B) multiple player bullets collide and kill enemy | A) Shoot a bullet when an enemy is near wall so that it collides both the enemy and wall, and B) Turn shotgun shots on, then walk up to a low health enemy and shoot
6 - game pause IO | 2024-10-07 | 2024-10-12 | P4 | Resolved | Sky, Amanda | when game is paused, some button presses will still process after game unpauses | when game is paused, no keys pressed should be processed after game is unpaused | pressing space/E while game is paused will make player dash/pull up dialogue after game is unpaused | press esc, then press space/E
7 - Text Overflow | 2024-10-09 | 2024-10-20 | P4 | Open | Amanda | If text is too long in dialogue box, will fly off screen | Text should wrap around to next line in dialogue box if too long; if entire text block is too long for box, should somehow be flagged to script writer | Text doesn't know when it's too long and flies off of box, so it gets cut off | press E to pull up dialogue box. On most monitors (1920 x 1080), the last dialogue line will be too long and gets cut off
8 - enemy wall clipping | 2024-10-13 | 2024-10-20 | P3 | Open | Vincent | although enemy is confined within boundary of screen, will currently clip through the boundaries slightly | There should be some offset to enemy position so that the enemy sprite won't clip through boundaries of screen | enemy sprite clips through screen boundary walls | wait for enemy to approach walls if movement is random
9 - shooting delay/unresponsiveness | 2024-10-13 | 2024-10-13 | P4 | Resolved | Dean | slight delay between pressing shoot and the actual bullets shooting for player | player shooting should be responsive and have no delay | quickly clicking LMB to shoot sometimes does not shoot anything; there is a delay in bullets being shot when pressing and holding LMB | click/press and hold LMB
10 - sprite offset | 2024-10-12 | 2024-10-20 | P3 | Open | Amanda | enemy sprite not centered, so the collision circles do not match well with sprite | enemy sprite should be centered so that the center of the collision circle and the sprite match | enemy collision circle is offset from enemy sprite | look at the enemy
11- Screen flicker | 2024-10-13 | 2024-10-20 | P4 | Open |  | Screen flickers when adjusting volume in windows. Might have to do with GLFW configurations | Screen ideally never flickers | Screen briefly flickers when volume up/down/mute are pressed | Adjust volume while playing game in windows; not sure if is on mac
12- Bullet wall collsion effect appearing through walls | 2024-10-13 | 2024-10-20 | P4 | Open |  | The particles generated by a bullet colliding with a wall can sometimes appear on the other side of the wall | all particles stay on the side of the wall that the bullet collided with | particles are sometimes generated on the opposite side of the wall due to the random nature of their spawning code | shoot into walls a ton